## Key
Categories: | Associated Letter:
Administrative Stuff | A | ID Structure:
Github | B | First Letter be Category
Research | C | First Number be Feature Number
Landing Page | D | Period
Grid and Tiles | E | Additional Numbers are PBI#
Game Logic | F
Bug Fixes | G

## Req. Traceability Matrix
Requirements Traceability Matrix - Mineswepper
Requirement ID: | Requirement Description: | Associated PBI ID: | Associated PBIs: | Associated Sprint: | Contributor: | PBI Status: | Notes:
B1 | Github
|  | B1.1 | Create Github Repo | 0 | Tyler Campbell | Done
|  | B1.2 | Setup Github Rules | 0 | Tyler Campbell | Done
|  | B1.3 | Add Contributors to Github | 0 | Tyler Campbell | Done
|  | B1.4 | Clean Repo for Sprint 1 | 0 | Chris Powers | Done
C1 | Research Stories
|  | C1.1 | Javascript Research Story - Tyler Campbell | 1 | Tyler Campbell | Done
|  | C1.2 | Javascript Research Story - Zach Farmer | 1 | Zach Farmer | Done
|  | C1.3 | Javascript Research Story - Chris Powers | 1 | Chris Powers | Done
|  | C1.4 | Javascript Research Story - Nathan Mink | 1 | Nathan Mink | Done
|  | C1.5 | Javascript Research Story - Christian Rock | 1 | Christian Rock | Done
|  | C1.6 | Javascript Research Story - Scotty Snyder | 1 | Scotty Snyder | Done
|  | C1.7 | Javascript Research Story - Gavin Frisby | 1 | Gavin Frisby | Done
|  | C1.8 | Documentation of Prototype from Research Project - Zach Farmer | 2 | Zach Farmer | Done
D1 | Landing Page that Hosts the Game
|  | D1.1 | Create HTML, Javascript, and CSS Files for the Landing Page with the Game Name. | 1 | Christian Rock | Done
D2 | Game Name on Landing Page
|  | D1.1 | Create HTML, Javascript, and CSS Files for the Landing Page with the Game Name. | 1 | Christian Rock | Done
D3 | Dev Team Names on Landing Page
|  | D3.1 | Add Name to Landing Page - Tyler Campbell | 1 | Tyler Campbell | Done
|  | D3.2 | Add Name to Landing Page - Zach Farmer | 1 | Zach Farmer | Done
|  | D3.3 | Add Name to Landing Page - Chris Powers | 1 | Chris Powers | Done
|  | D3.4 | Add Name to Landing Page - Nathan Mink | 1 | Nathan Mink | Done
|  | D3.5 | Add Name to Landing Page - Christian Rock | 1 | Christian Rock | Done
|  | D3.6 | Add Name to Landing Page - Scotty Snyder | 1 | Scotty Snyder | Done
|  | D3.7 | Add Name to Landing Page - Gavin Frisby | 1 | Gavin Frisby | Done
|  | D3.8 | Comment out the button for the rules page. Add PO and Scrum Master to List of Names on Landing Page under a Credits section.
D4 | Frame within Landing Page that Contains the Game
|  | D4.1 | Create Div for Game Frame on Landing Page and do CSS for Frame (Incorporate Outline) | 2 | Scotty Snyder | Done
|  | D4.2 | Display the Grid Inside of the Frame on the Page | 2 | Christian Rock | Done
|  | D4.3 | Ensure that the game frame adjusts within the Index HTML based on the device. (Portrait and Flipped) |  |  | To Do
D5 | List the Game Rules on the Landing Page
|  | D5.1 | List the Game Rules on the Landing Page | 2 | Chris Powers | Done
E1 | Create fixed x by y Grid
|  | E1.1 | Create 10 X 10 grid where each cell is populated by a tile instance. | 2 | Christian Rock | Done
E2 | Create Tile Type Class
|  | E2.1 | Create Tile type class with the properties for each possible tile. | 2 | Christian Rock | Done
|  | E2.2 | Each Tile is represented by an instance of the tile object. | 3 | Tyler Campbell | Done
E3 | Ability to Interact with the Tiles
|  | E3.1 | Ability to Interact with the Tiles | 2 | Tyler Campbell | Done
E4 | Ability to Generate the Grid
|  | E1.1 | Create 10 X 10 grid where each cell is populated by a tile instance. | 2 | Christian Rock | Done
D6 | A UI within the Frame that Displays Information
|  | D6.1 | Creation of a UI bar that would allow swapping between clicking, flagging, etc. |  |  | To Do
|  | D6.2 | Creation of a UI bar that would display the number of bombs, number of flags used, and the timer. |  |  | To Do
A5 | Create Graphic for Carousel
|  | A5.1 | Create a 400x400 PNG Image to be used for website carousel. | 2 | Tyler Campbell | Done
E5 | Ability to Populate the Grid
|  | E2.2 | Each Tile is represented by an instance of the tile object. | 3 | Tyler Campbell | Done
A3 | Color Scheme for the Game
|  | A3.1 | Create and Document a Color Scheme for the Game | 2 | Chris Power | Done
|  | A3.2 | Apply the Color Scheme to the Grid and Tiles | 2 | Nathan Mink | Done
A2 | Create a State Diagram going through each Tile State/Type
|  | A2.1 | Create a State Diagram going through each Tile State/Type | 3 | Gavin Frisby | Done
D7 | Develop page/game frame refresh.
|  | D7.1 | Develop page/game frame refresh. | 2 | Zach Farmer | Done
F1 | Time Keeping in Game
|  | F1.1 | Timer in UI with functionality (starts on first click, 3 characters max, stops when game ends). | 3 | Nathan Mink | Done
E6 | Ability to Flag a Tile
|  | E6.1 | Develop flag functionality for flag tiles. | 3 | Christian Rock | Done
E7 | Ability to Unflag a Tile
|  | E6.1 | Develop flag functionality for flag tiles. | 3 | Christian Rock | Done
E8 | Ability to Question a Tile
|  | E8.1 | Develop question functionality for question tiles (reskinned flags). |  |  | To Do
E9 | Ability to Unquestion a Tile
|  | E8.1 | Develop question functionality for question tiles (reskinned flags). |  |  | To Do
E10 | Ability to Reveal a Tile
|  | E3.1 | Ability to Interact with the Tiles | 2 | Tyler Campbell | Done
F2 | Ability to Swap Touch Functionality between Flagging, Revealing, Questions
|  | F2.1 | Functionality of the UI bar that changes what clicking does. |  |  | To Do
E11 | Different Tile Types (Unrevealed, Bomb, Clear, Number, Flag, Question)
|  | E3.1 | Ability to Interact with the Tiles | 2 | Tyler Campbell | Done
|  | F4.1 | Develop bomb functionality for bomb tiles. | 3 | Scotty Snyder | Done
|  | E6.1 | Develop flag functionality for flag tiles. | 3 | Christian Rock | Done
|  | E8.1 | Develop question functionality for question tiles (reskinned flags). |  |  | To Do
|  | E11.1 | Develop number functionality for number tiles (including ones with 0 bombs). | 3 | Tyler Campbell | Done
|  | E11.2 | Revealing a 0 will reveal any adjacent 0s and their adjacent number tiles. | 4 | Nathan Mink | Done
A6 | Ability to Test Game
|  | A6.1 | Create Unit Tests and Test Plans for Sprint 2 functionality. | 3 | Chris Powers | Done
|  | A6.2 | Add Minesweeper.js Unit Tests |  |  | To Do
|  | A6.3 | Modify selenium file to test key functions of the program like flag, unflag, and playing the game until the end. | 4 | Christian Rock | Doing
F3 | Game Winning Logic - Ends in a Win whenever all Non-Bomb Tiles are Revealed
|  | E11.1 | Develop number functionality for number tiles (including ones with 0 bombs). | 3 | Tyler Campbell | Done
|  | F3.1 | Game Winning Logic - Ends in a win if all non-bomb tiles are revealed. Stops the timer. | 4 | Tyler Campbell | Doing
F4 | Game Losing Logic - Ends in a Loss whenever a Bomb Tile is Revealed
|  | F4.1 | Develop bomb functionality for bomb tiles. | 3 | Scotty Snyder | Done
F5 | Game Logic - Revealed Tiles that Aren’t Mines Display Number of Adjacent Mines
|  | E11.1 | Develop number functionality for number tiles (including ones with 0 bombs). | 3 | Tyler Campbell | Done
E12 | Ability to Randomly Generate Mines
|  | E12.1 | Ability to generate which tiles a mine will be placed at. | 2 | Tyler Campbell | Done
F6 | Leaderboard based on Score with Ability to Leave Initials
|  | F6.1 | Gather three initials from the user to pass to the leaderboard. |  |  | To Do
E13 | Ensure Mines are Not Placed on the Same Tile
|  | E12.1 | Ability to generate which tiles a mine will be placed at. | 2 | Tyler Campbell | Done
F7 | Game Logic - The First Click Cannot Reveal a Mine
|  | F7.1 | Develop first click logic. | 3 | Zach Farmer | Done
E14 | Cannot Reveal a Tile that has been Flagged unless Flag is Removed
|  | E6.1 | Develop flag functionality for flag tiles. | 3 | Christian Rock | Done
F8 | Display the Number of Flags Used
|  | F8.1 | Counter that displays the number of flags used. | 4 | Zach Farmer | Doing
F22 | Display the Number of Mines
|  | F22.1 | Counter that displays the number of mines. | 4 | Gavin Frisby | Doing
F9 | Difficulty Levels that Change the Size of the Grid and the Number of Mines
|  | F9.1 | Difficulty levels that change the number of mines in the grid. |  |  | To Do
F10 | Custom Difficulty where User can Select the Size and Number of Mines
|  | F10.1 | Custom Difficulty that allows the user to specify the number of mines (with minimums and maximums). |  |  | To Do
F11 | Customization Options like Board Color and Theme
F12 | Validation for Score and Initials for Leaderboard
|  | F6.1 | Gather three initials from the user to pass to the leaderboard. |  |  | To Do
F14 | Ability to Restart at any Time (New Grid and Mine Placement)
|  | D7.1 | Develop page/game frame refresh. | 2 | Zach Farmer | Done
F15 | Sound Effects
F16 | Ability to Zoom In and Out
F17 | Counter for Number of Clicks
|  | F17.1 | Counter that displays the number of revealed tiles. | 4 | Nathan Mink | Doing
F19 | Ability to Automatically Reveal All Tiles (Not Sent for Leaderboard)
|  | F19.1 | Button to automatically display all of the tiles/give up. Disables saving score for leaderboard. |  |  | To Do
F20 | End Screen with Score, Time, Clicks, Replay Button
|  | F20.1 | End screen that displays whether you won or lost, the number of clicks taken, the score, the time taken, and the ability to play again. |  |  | To Do
A1 | Project Automation
|  | A1.1 | Create Automation to Add Reviewers for Github Pull Requests | 1 | Tyler Campbell | Done
A7 | UML Class Diagram
|  | A7.1 | UML Class Diagram for Tile Object | 3 | Gavin Frisby | Done
A8 | Transition Document for Future Teams
|  | A8.1 | Create a transition document for future development teams. | 4 | Chris Powers | Doing
|  | A8.2 | Update existing documentation with changes in preparation for Transition |  |  | To Do
|  | A8.3 | Documentation of Test Cases |  |  | To Do
G1 | Bug Fixes
|  | G1.1 | Fix Bug where a Flagged bomb tile being clicked will still cause the game to end (image attached). | 4 | Zach Farmer | Done
|  | G1.2 | Fix Tile.js Unit Tests | 4 | Chris Powers | Done